## Sheet1
Onboarding Customer Success Plan
Ref | Phase | Work Segment / Tasks | Status | Team Members | Deliverable | Note
1 | Client Discovery Questionnaire | Day 1 - Client Completed - Channels, Setup, Goals | Open | Client | Hub Spot Email | CS Lead Assigned
1a | Set Up - myFinLocker | Branding - Browser Setup | Open | Client - Marketing | Branded myFinLocker | Browser version
1b | Set Up - myFinLocker | Determine Product Name/Logo | Open | Client - Marketing | Branded myFinLocker | Optional
1c | Set Up - myFinLocker | Review Changes | Open | Client - Marketing - FL CS Team | Branded myFinLocker
1d | Planning and Communication | Pre-Meeting - Set Up Key Links | Open | Joint |  | Sponsor Team
1e | Planning and Communication | Pre-Meeting - Send Intro Email - Link, Admin | Open | Joint |  | Sponsor Team
1f | Set Up - myFinLocker | Send myFinLockers/Admin to Users | Open | Joint | User Rollout
2 | Planning and Communication | Kickoff Meeting - Customer Success | Open | Joint - Leads | Pilot scope and plan | Plan for 2 Weeks Out
2a | Planning and Communication | Timing, Goals, Metrics | Open | Joint |  | Sponsor Team
2b | Planning and Communication | Identify Rollout Personas/Steps | Open | Joint
2c | Planning and Communication | Marketing / Consumer Outreach | Open | Joint | Marketing Messaging | Post Financial Locker Follow Up
2d | Planning and Communication | Key Stakeholders Roles | Open | Joint | Key Contact List
2e | Planning and Communication | Next Meeting - 2 Weeks Out, Customer Review | Open | Joint | Key Contact List
2f | Planning and Communication | Post-Meeting Summary email | Open | Joint | Marketing Messaging | Post Financial Locker Follow Up
2g | Planning and Communication | Post-Meeting Add Team to User Community Group | Open | Joint | Key Contact List
2h | Set Up - myFinLocker | Demo - Training - User Rollout Planning | Open | Joint | User Training | User Guides Shared
2i | Set Up - myFinLocker | Branding - Mobibe ANDROID App Setup | Open | Client - Marketing | Android Mobile App | Provided to the FL CS, Set up Guide
2j | Set Up - myFinLocker | Review Andriod Application | Open | Joint | Android Mobile App
2k | Set Up - myFinLocker | Branding - Mobibe APPLE App Setup | Open | Client - Marketing | Android Mobile App | Provided to the FL CS, Set up Guide
2l | Set Up - myFinLocker | Compliance review of material | Open | Joint/Compliance |  | Optional
2m | Set Up - myFinLocker | Approval - FinLocker Support (Admin) | Open | Client - Sponsor
2n | Set Up - myFinLocker | Integratiions - Planning | Open | Joint
2o | Set Up - myFinLocker | CRM Integration - Automation | Open | Joint/Marketing | Distribution myFinLocker
2p | Set Up - myFinLocker | Loan Sharing Integrations - Technical | Open | Joint/Tech Support/Integrations | I'm Ready
2q | Rollout 1 - Employees/Users | Planning/Meeting | Open | Joint - Leads
2r | Rollout 2a - Persona 1 | Planning/Meeting | Open | Joint - Leads |  | FHA/Housing, FreddieMac
2s | Rollout 2b - Persona 2 | Planning/Meeting | Open | Joint - Leads |  | Consumer Engagement
2t | Rollout 2c - Persona 3 | Planning/Meeting | Open | Joint - Leads |  | Potential Integration ???
3 | Planning and Communication | Client Review | Open | Joint - Leads | Joint Score Card
3a | Customer Success | Ongoing Candence/Customer Review Meeting | Open | Joint - Leads | Status, Metrics | Rollout, Monthly/Quarterly (Steering)
3b | Customer Success | Pipeline Reporting and Metrics | Open | Joint - Leads | Metrics